## Sheet1
2018-04-03
| No of test case executed | Modules | Defects created
| Platform = QA3[Hanes-Chrome] Executed TC count = 18 | Change Password (Complete) Search Result (In Progress) Checkout (In Progress) Shopping Cart (Completed) | HNS-4805 HNS-4812 HNS-4813 HNS-4814 HNS-4815 HNS-4817 HNS-4818 HNS-4822 HNS-4823 HNS-4824
2018-04-04
| No of test case executed | Modules | Defects created
| Platform = QA3[Hanes-Chrome] Executed TC count = 20 | Change Password (Complete) Search Result (In Progress) Checkout (In Progress) Shopping Cart (Completed) | HNS-4825
2018-04-05
| No of test case executed | Modules | Defects
| Platforms:- a) QA3(Hanes-Chrome) b) QA3 (One Hanes Place-Chrome) Executed Test Case Count = 40 | Hanes-Chrome:- Search Result (Completed) Checkout (Completed) One Hanes Place-Chrome:- My Profile (Completed) Shopping Cart (Completed) Search Result (In Progress) Checkout (Yet to start) | Created:- HNS-4829 HNS-4831 Re-tested:- HNS-4812 HNS-4822 HNS-4823
| Platform | Total | Not Run | [%] | Passed | [%] | Failed | [%] | Blocked | [%] | Completed [%]
| Hanes-Chrome | 57 | 2 | 3.5 | 48 | 84.2 | 7 | 12.3 | 0 | 0 | 96.5
| OHP-Chrome | 57 | 36 | 63.2 | 20 | 35.1 | 1 | 1.8 | 0 | 0 | 36.8
2018-04-06
| No of test case executed | Modules | Defects
| Platform:- QA3 (One Hanes Place-Chrome) Executed Test Case Count = 32 | One Hanes Place-Chrome:- My Profile (Completed) Shopping Cart (Completed) Search Result (In Progress) Checkout (Completed) | Created:- HNS-4832 HNS-4833
| Platform | Total | Not Run | [%] | Passed | [%] | Failed | [%] | Blocked | [%] | Completed [%]
| OHP-Chrome | 57 | 4 | 7 | 51 | 89.5 | 2 | 3.5 | 0 | 0 | 93